## Sheet1
Milestone | Date | Weighting (%)
Get Q-values for each model | 2016-09-22 | 5
Implement multivariate model ("model 3") | 2016-09-22 | 5
TDD check | 2016-09-22 | 5
TDD check | 2016-09-29 | 5
TDD check | 2016-10-06 | 5
Modularisation complete | 2016-10-06 | 10
Potentially shippable (code to Sanjid, he can run and use) | 2016-10-13 | 10
TDD check | 2016-10-13 | 5
Code completion check | 2016-10-18 | 15
Documentation finalised | 2016-10-18 | 5
TDD check | 2016-10-20 | 5
Code finalised | 2016-10-20 | 10
Demonstration – All tests should pass | 2016-10-27 | 5
Final Project Report | 2016-10-27 | 10
100