## Sheet1
Milestone	Date	Weighting (%)	Done?
Get Q-values for each model	22/09/16	5	Y
Implement multivariate model ("model 3")	22/09/16	5	Y
TDD check	22/09/16	5	Y
TDD check	29/09/16	5	Y
TDD check	06/10/16	5
Modularisation progress check	06/10/16	5
Modularisation complete	13/10/16	5
Potentially shippable (code to Sanjid, he can run and use)	13/10/16	10
TDD check	13/10/16	5
Code completion check	18/10/16	15
Documentation finalised	18/10/16	5
TDD check	20/10/16	5
Code finalised	20/10/16	10
TDD check	27/10/16	5
Final Project Report	27/10/16	10
		100